## Summary
UI Consistency Audit - Round 2
Date | 2026-10-10
Findings | 92
P0 | 1
P1 | 31
P2 | 48
P3 | 12
Estimated effort (dev-days, upper bound) | 244
Behaviour | 20
Structure | 15
Content | 15
Visual | 14
Data/config | 14
Accessibility | 14

## Finding register
ID | Area | Severity | Effort | Finding | Evidence (path:line) | Recommendation | Status | Resolution
A-30 | Accessibility | P0 | M | Select listbox model is unusable by screen readers (shared by PhoneNumberInput and FilterSelect) | Select.tsx:159-172,208-231 (focus to a bare ul, no option ids/aria-activedescendant/aria-controls/name, no focus return, no Home/End/type-ahead, no scrollIntoView, error not linked); PhoneNumberInput.tsx:198-215; C360Kit.tsx:356-430 | One Listbox primitive (round-1 A-06). | Fixed | Select, PhoneNumberInput, FilterSelect: aria-controls, aria-activedescendant, option ids, scrollIntoView, Home/End/PageUp/PageDown, type-ahead, focus return, error linked. Verified in the browser.
A-31 | Accessibility | P1 | M | Customer/service actions menu is not keyboard operable | CustomerActionsMenu.tsx:103-130,166 (portal far from trigger, no focus in, no arrows, no aria-controls, highlight 1.06:1, no focus return) | Shared Menu with roving focus. | Fixed | Actions menus: focus moves in, arrows/Home/End, Esc/Tab close and return focus, aria-controls, visible highlight. Verified in the browser.
A-32 | Accessibility | P1 | M | Choice cards do not expose their selected state; interactive children sit inside role=button/radio | QidInput.tsx:158-186, CafSignatureCapture.tsx:355-372, BillingAccountStep.tsx:122, ProductPlanStep.tsx:76 (no aria-pressed/checked); PostpaidPlanCard.tsx:32+:104, CrossSalesStep.tsx:137+:190, DataTable.tsx:190 (role=button tr hides cell controls); ~9 hand-copied card variants | SelectableCard primitive (button aria-pressed or native radio/checkbox in fieldset). | Partly | aria-pressed on ID-type, CAF-type, plan and billing-account cards; clickable table rows no longer role=button. Plan cards still nest a button inside role=button; no shared SelectableCard primitive yet.
A-33 | Accessibility | P1 | S | Input/Select/Textarea derive ids from the label (input-undefined, duplicates); six selects unnamed; errors not announced | Input.tsx:40, Select.tsx:65, Textarea.tsx:10; PersonaSwitcher.tsx:282-287, TicketActionsCard.tsx:52, TicketsDashboard.tsx:245,252,258, TaskDetailView.tsx:161; Textarea.tsx:12-42, Input.tsx:178, QidInput.tsx:265-328, LoginPage.tsx:165-179 lack role=alert/aria-invalid/describedby | useId, FieldError with role=alert, label¦aria-label required (round-1 A-07/A-08). | Partly | useId for Input/Select/Textarea; errors are role=alert and linked; six unnamed selects named. A label-or-aria-label requirement is not enforced by types.
A-34 | Accessibility | P1 | S | Login carousel auto-advances with no pause; off-screen slides keep a focusable Read-more button; dots are tabs without panels | LoginAnnouncements.tsx:70-75,92-93,118,133-144 | Pause/play, focusin pause, reduced-motion stop, inert off-screen slides (round-1 A-10). | Fixed | Pause/Play, pause on hover and focus, reduced-motion start state, off-screen slides inert, dots are buttons with aria-current.
A-35 | Accessibility | P1 | S | Tooltip-only information on non-focusable triggers; Badge cannot hold a tooltip | SessionReferenceNumbers.tsx:359,406,427,475; HeaderContextChips.tsx:64,83; InvoiceActions.tsx:31; ProductActionGroups.tsx:156; tooltip.css pointer-events:none | Tooltip adds tabIndex=0 and a hoverable surface; forward refs in Badge (round-1 A-13). | Fixed | Tooltip makes text/badge triggers focusable and the tip hoverable (120ms hide delay); Badge forwards props and ref.
B-01 | Behaviour | P1 | S | createRecord appends to an array the engine already mutated, so created rows can show twice (or hide the seed rows) | stores/entityStore.ts:22-47; engines/mockDataEngine.ts:81-99 (list returns the engine's own array, create pushes into it, store appends again; an unloaded kind caches only [new] and loadKind then returns early). ~30 createRecord call sites. Confirmed by code reading, not reproduced in the browser. | Clone in list(), or make the store the only writer; never early-return loadKind on a partial cache. Add a test. | Fixed | list() returns a copy; createRecord only extends an already-loaded list.
B-02 | Behaviour | P1 | S | Lead details fall back to the first lead when the id is unknown | modules/lead-management/LeadDetailsView.tsx:51 (find(...) ?? leads[0]) - verified. An agent can reject or reassign the wrong lead. | Missing record = not found, not-yet-loaded = loading; one EntityScreen / useEntityById. | Fixed | Fallback removed; unknown id is "not found" (EntityMissing).
B-04 | Behaviour | P1 | S | Sign-out and role switch discard an in-progress journey with no confirmation | navigation/PersonaSwitcher.tsx:290,87; stores/authStore.ts:46; resetSession uses location.replace so useBlocker never fires; no beforeunload | Confirm when a draft or active customer exists; beforeunload for dirty wizards. | Fixed | Sign-out and role switch ask first when a journey has progress; beforeunload warns on tab close.
B-05 | Behaviour | P1 | M | No shared async-state contract: loading / empty / error handled differently per screen | ~50 mockDataEngine.list().then(setX) chains with no catch; infinite 'Loading…' at BillingAccountPage.tsx:91 and Customer360Layout.tsx:146; error shown as not-found (Customer360Layout.tsx:176, CustomerSearchResults.tsx:70); DataTable empty flash before load | useAsyncData + AsyncBoundary (loading/empty/error+retry); entityStore sets loading synchronously. | Partly | Load-failed state with Try again on Customer 360 and billing account; tables use useKindPending (no empty flash); entityStore error text is plain. The ~50 other list().then chains are not yet on a shared useAsyncData.
B-06 | Behaviour | P1 | M | Mutations have no submit guard or failure handling; Save buttons stick on 'Saving…' | No guard: LeadDetailsView.tsx:59-81, SimSwapQueueScreen.tsx:92,101, TaskDetailView.tsx:95-121, ticketDetailActions.ts (all), BillingAccountPage.tsx:131, useWizardDraftActions.ts:85 (double Abandon = two activities). setSaving never reset on failure: DemographicEditDrawer.tsx:44-64, AddressSection.tsx:147-155, ContactSection.tsx:136-144 | useSubmit(fn) with ref guard, try/catch, toast on failure, always reset. | Partly | useSubmit / useSubmitGuard added; applied to the three edit drawers, lead, SIM swap, ticket actions, task detail, billing account; wizard end-of-journey actions guarded. Other mutations still unguarded.
D-01 | Data/config | P1 | S | CI never runs: workflow sits under vfq-dxp-app/ but the git root is one level up | vfq-dxp-app/.github/workflows/ci.yml (untracked); git root is /Users/.../vfq; confirmed no ../.github | Move to <root>/.github/workflows/ci.yml and commit (also fix CLAUDE.md claim). | Open | Blocked: the sandbox cannot create <repo root>/.github. Run: mkdir -p ../.github/workflows && cp .github/workflows/ci.yml ../.github/workflows/ci.yml
D-02 | Data/config | P1 | M | RBAC is presentational: the router has no guard; 33 of 50 feature keys are never enforced | router.tsx:62-100, ScreenRouteResolver; only workspace.customer-search, workspace.admin-role-access-viewer, journey featureKeys and canPerformAction(SCR-061) are enforced; /administration, /sales, /orders, /support, /leads and any module URL open for every role | RequireFeature wrapper using canUseFeature; or label the matrix informational. | Open | Decision needed: enforce grants on routes (hides ~50 destinations from roles that see them today) or label the matrix informational.
D-03 | Data/config | P1 | M | Sidebar follows approach, not grants: ~50 role/nav mismatches | navigationEngine.ts:29-46 vs personas.json (e.g. ROLE-09/16/17/19 see sales/support/orders without grants; ROLE-14/15 hold orders/customer-search with no nav item; Customer-First roles hold leads.list-views with no Leads item) | Gate nav items on their feature keys or document nav as IA-only; add a parity test. | Open | Decision needed with D-02.
D-04 | Data/config | P1 | S | Unknown URLs do not reach NotFound; /mobile/:category accepts anything; /mobile/new-connection vs /mobile/new-connections | ModuleScreenList.tsx:~66, ScreenNotYetBuilt.tsx:17-24, router.tsx:74,76,99-101, 72 | NotFound for unknown module/screen/category; rename the wizard URL. | Fixed | NotFound for unknown module, screen and category; wizard URL renamed /mobile/start-connection.
D-05 | Data/config | P1 | S | validateJourneyCatalogue() is described as a guard but does not exist | navigation/journeyCatalogue.ts:25; only the Python matrix builder checks it; mob-new-connection is 'available' with no featureKey (:~84) | Implement and test it. | Fixed | validateJourneyCatalogue() implemented and tested (it found no live errors once list-registered screens were counted).
D-06 | Data/config | P1 | S | Mock identity data contradicts itself for the QA customers | CUST-1001 customers.qid 28512345678 vs identity-documents 28456701234; CUST-1002 P-N1234567 vs P0998812; CUST-2001 QID 28855544433 vs 'Other ID' RES-7788221; CUST-9001 idType QID with value P1234567 and a second Passport doc - verified; CUST-9001 is 16 years old | One document row per customer.qid/idType; adult QA identity. | Open | Decision needed: which ID is canonical per QA customer (already logged as Q6 in the customer inventory). Customer-Inventory.xlsx on disk was re-saved by Excel and is no longer readable by the generator.
D-09 | Data/config | P1 | M | No session timeout despite comments claiming one; auth persists in localStorage; no cross-tab sign-out | resetSession.ts:3 and authStore.ts:45 mention it; WinCashPaymentStep.tsx:19 admits none exists; no storage listener | Idle timer + storage event, or remove the comments. | Partly | Comments no longer claim an idle timeout; sign-out in one tab signs out the others. No idle timeout implemented.
S-01 | Structure | P1 | S | Import cycle across 9 files (barrel bypass) | components/patterns/GuidedContactStep.tsx:5, MoiResultPanel.tsx:3 import from '../../capabilities' barrel; VerificationGate.tsx:8; capabilities/CustomerIdentification/*, CustomerQualification/* | Import IdentityDetailsCard from its file; add a no-cycle test. | Fixed | Drawer and offer-card parts moved to components/primitives; capabilities no longer imported by primitives; architecture test enforces layers.
S-02 | Structure | P1 | M | Layer violations: components import workspace; capabilities<->components both ways; workspace imports modules and vice versa | StepSummaryPanel.tsx:3 (fmtDate from workspace/C360Kit); customerActions.ts:3, useStartNewConnection.ts:2, MobileSection.tsx:7; ProductLinePage.tsx:10; LocationInput.tsx:3 (primitive imports engine); 20 components->capabilities and 120 capabilities->components imports | Direction: primitives -> domain -> capabilities -> patterns -> modules/workspace; move Drawer and offerCardParts to primitives; move shared helpers to lib/navigation. | Fixed | No import cycles (tests/architecture.test.mjs); components no longer import workspace/modules.
S-03 | Structure | P1 | S | Hard-coded order actors and channels: orders by one persona are attributed to another | createdBy 'AGENT-VINODHINIR' (submitFixedActivationOrder.ts:70, submitPrepaidOrder.ts:110, QueryFlowCard.tsx:134), 'AGENT-KARTHIKK' (submitNewConnectionOrder.ts:177, NewFwaWizard.tsx:30), 'AGENT-HEMANTHKUMAR' (NewMnpWizard.tsx:89), 'current-agent' (2) - verified; sourceChannel Tablet vs Desktop | Take from the signed-in persona. | Fixed | currentAgentId() replaces every hard-coded createdBy.
S-04 | Structure | P1 | S | Closed-status sets disagree in 8+ places | Customer360Layout.tsx:70, accountInformationResolvers.tsx:22, C360AlertsRisks.tsx:28, C360TicketsSupport.tsx:33-34, C360AddressService.tsx:15, C360Overview.tsx:19, TelesalesOrdersTicketsSection.tsx:31,57, ruleEngine.ts:285 (only Closed/Cancelled) | isClosedTicket / isTerminalStatus in lib/statusTone.ts. | Partly | isClosedTicket / isSlaStopped in lib/statusTone; slaEscalationSweep.ts and useZoneMetrics.ts still use local sets.
V-01 | Visual | P1 | M | Title and heading styles: 5 sizes for page titles, 18/20/24px and 600/700 for card titles, KPI numbers in 4 styles | h1: h4 in PageHeader.tsx:28 and CustomerProfileHeader.tsx:157; h3 in WizardTitleBand.tsx:64, LeadDetailsView.tsx:93, TicketHeaderCard.tsx:19, OrderConfirmationScreen.tsx:83, NotFound.tsx:10, NotYetBuiltPanel.tsx:28, ErrorBoundary.tsx:45; clamp() in Dashboard.tsx:146. Card h2 at 24px in C360Kit.tsx:166, CapabilityLibrarySection.tsx:38, OfferDetailsDrawer.tsx:173. KPI: DashboardZone.tsx:164, Dashboard.tsx:156, MetricCard.tsx:8, TicketsDashboard.tsx:220 | Role table in report section 7 (round-1 L-01/L-02 still open). | Partly | Content-page h1 now 24px (--fs-h4); card h2 at 20px (--fs-h5). Hero/status headings and KPI numbers not yet unified.
V-02 | Visual | P1 | M | Wizard and detail grids use viewport breakpoints inside a 280px-sidebar + 352px-summary frame | Step card inner width = viewport - 746: 278px at 1024, 534px at 1280. CustomerTypeStep.tsx:78,84,115; CrossSalesStep.tsx:120; AddonsPicker.tsx:130; PostpaidDiscountsPanel.tsx:84; PlanGroupPanel.tsx:28; SimTypeStep.tsx:64; QidInput.tsx:143; CafSignatureCapture.tsx:350; CheckoutSummaryTables.tsx:15; FixedStepViews.tsx:55,183; LeadDetailsView.tsx:89,123; TicketDetail.tsx:74,101; OrderApprovalDetail.tsx:324,396; DashboardZone.tsx:153 | @container on the step card/page wrappers and @md/@lg/@xl, or auto-fill minmax grids (round-1 L-09). | Partly | Wizard step grids use auto-fill minmax columns (follow the panel width, not the window). Page-level grids (lead, ticket, order approval, dashboard zone) unchanged.
V-03 | Visual | P1 | S | Known 1024px defects confirmed in code: top-bar overlap, number-card clipping, identity-card date wrap | PersonaSwitcher.tsx:101 (1fr track resolves to ~0 with the strip and right cluster; overlap persists to ~1700px with an active ticket), SessionReferenceNumbers.tsx:344; MsisdnPicker.tsx:500-508,560,575,613 (~83px for a 2x2 fact grid); IdentityDetailsCard.tsx:33-39 (grid-cols-3 + break-words) | Strip only at xl: and move it to the breadcrumb row below; container-query grids; whitespace-nowrap on dates (round-1 L-10). | Fixed | Top-bar grid cannot overlap (verified at 1024); number cards and identity facts follow their panel width.
V-04 | Visual | P1 | M | No control-height scale: Button 39.6, Input 42, SearchField 50, --field-height 48, steppers 42, hero search ~58 | Button.tsx:97-181, Input.tsx:143, SearchField.tsx:37, tokens.css:518 (--field-height 3rem vs comment 42px), BillLimitEditor.tsx:74-81, GlobalSearch.tsx:228; misaligned rows at AgentProfileWorkspace.tsx:294, EnterpriseAccountCreation.tsx:63, TicketsDashboard.tsx:235 (8px) | sm 32 / md 42 / lg 48 tokens; SearchField size prop; min-h per Button size. | Partly | --control-h-sm/md/lg scale; Button, Input and SearchField use it (verified aligned on Tickets Dashboard). Hero search and steppers unchanged.
V-09 | Visual | P1 | M | Dark mode: white text on success/danger fills fails contrast; field borders 1.76-1.98:1; dash-card shadows have no dark value; SignaturePad ink follows the theme | bg-success 2.11:1 (OrderConfirmationScreen.tsx:80, C360AddressService.tsx:160), bg-danger 3.44:1 (Button.tsx:165, CustomerProfileHeader.tsx:198); --shadow-dash-card(-hover) in tokens.css; SignaturePad.tsx:38,55 stores a transparent PNG with theme ink (near-white in dark) used by CafSignatureCapture.tsx:244,396, DonorAttachmentStep.tsx:50, SimSwapFormStep.tsx:29 | *-solid tokens for filled status; dark shadow values; fixed dark ink on a white backing. | Fixed | --success-solid / --danger-solid for filled status; dark shadows; dark field borders at 3:1; signature ink fixed dark on a white pad.
X-02 | Content | P1 | S | 'Cancel' means dismiss in 33 places and 'cancel the ticket' in one | TicketActionsCard.tsx:76 vs 33 dialog-dismiss uses | 'Cancel ticket'; Cancel = dismiss only. | Fixed | "Cancel" -> "Cancel ticket".
X-06 | Content | P1 | S | Prototype and requirement text visible to users | OfferDetailsDrawer.tsx:238 'not linked in the prototype'; TicketCreationModal.tsx:281 'BRSD dependency D-07'; ticketDetailActions.ts:242 'P-15 placeholder'; AgentProfileWorkspace.tsx:272,288 ('D-03', 'OI-AGN-07'); DemographicEditDrawer.tsx:98 '(DF-DEMO-001-007)'; BillingSection.tsx:35 'BRSD v3.1 Annex_01'; 'mock catalogue' x3 (PrepaidPlanStep.tsx:123, PostpaidPlanAddonsStep.tsx:155, FixedStepViews.tsx:238); ScreenNotYetBuilt.tsx 'blueprint' | Remove from visible text; keep in code comments. | Fixed | Prototype / requirement / BRSD text removed from visible strings; test-only buttons are demo-only (hidden with VITE_SHOW_DEMO=false).
X-07 | Content | P1 | S | Raw requirement text renders as field labels, with typos | TopicFieldsSection.tsx:171-276 renders field.details from customer360-fields.json: 'Billing Receipent', 'purschages', 'Actiivity (last 5)', 'Audit Trail (Orders,Contact, Account, Activity,TT)' | Display-label map; fix typos in the JSON. | Fixed | Typos fixed in config and code; fieldLabel() drops long explanatory brackets from displayed labels.
X-08 | Content | P1 | M | Raw catalogue names shown as breadcrumbs, search results and titles; h1, breadcrumb, journey label and tab title disagree on 20 of 25 sampled screens | routes.json: 110 of 213 screenName values carry a parenthetical (longest 107 chars); 'Target State', 'DXP', 'Applet', 'Siebel'; Breadcrumbs.tsx:93, GlobalSearch.tsx:275, ModuleScreenList.tsx:108, ScreenNotYetBuilt.tsx:21; screen ids printed in GlobalSearch.tsx:276 | displayName in routes.json used by all four surfaces and <title> (round-1 L-11). | Partly | screenDisplayName() used by breadcrumbs, search, module list and not-yet-built page; search shows the module, not the screen id. routes.json itself is unchanged.
X-09 | Content | P1 | S | Error messages expose exceptions and internal codes | entityStore.ts:36 ('Failed to load x: <message>'), OrderApprovalDetail.tsx:564, ErrorBoundary.tsx:45 'Something went wrong' | Plain language plus 'Try again'. | Fixed | entityStore, order approval, config boot and ErrorBoundary use plain language with Try again / Reload.
A-36 | Accessibility | P2 | S | Icon has no aria-hidden (185 uses); Spinner has no text; toast containers unmount when empty and sit after main | Icon.tsx:17; Spinner.tsx:41-43; Toast.tsx:155,167,186-190 | aria-hidden default; sr-only label; persistent live regions (round-1 A-14). | Open
A-37 | Accessibility | P2 | S | Login and password forms lack form semantics, autocomplete and a main landmark | LoginPage.tsx:149,164-217; ForgotPasswordFlow.tsx:97-125; AgentProfileWorkspace.tsx:203-205; only one <form> in the app (CustomerSearchPage.tsx:46) | form + submit, autocomplete=username/current-password/new-password/one-time-code (round-1 A-09). | Open
A-38 | Accessibility | P2 | M | Header popups declare menu semantics they do not implement; profile aria-label overrides the visible name; landmarks and breadcrumb are divs | PersonaSwitcher.tsx:189,232,252-253,197-297,101; Breadcrumbs.tsx:43,79 | Disclosure pattern with Escape/focus return; header/search/nav landmarks; nav>ol with aria-current (round-1 A-16). | Open
A-39 | Accessibility | P2 | S | DataTable and tab semantics: no caption/aria-busy/scope, hideHeader ignored on sortable columns, SegmentedTabs without tabpanel, vertical Tabs without roles | DataTable.tsx:133,146-180; SegmentedTabs.tsx:49-60; Tabs.tsx:59-79,130; CheckoutSummaryTables.tsx:17 (title as th colSpan) | caption/aria-label props, status for loading/empty, ids + aria-controls + tabpanel (round-1 A-17). | Open
A-40 | Accessibility | P2 | M | Reflow at 320px: drawer min-w 420px, grid-cols-3 forms without breakpoints, non-wrapping header | Drawer.tsx:61; 14 forms (GuidedContactStep.tsx:168, ZsbAddressStep.tsx:193,222, AddressSection.tsx:181, ContactSection.tsx:168, BillingAccountStep.tsx:229, ...); PersonaSwitcher.tsx:101; wizard m-8 p-6 | min-w-[min(420px,100%)]; shared FormGrid; responsive margins. | Open
A-41 | Accessibility | P2 | S | Combobox gaps shared by result-list searches: no blur close, Escape always swallowed, no result announcement, non-option li in listbox, dangling aria-controls, GlobalSearch/Sidebar search have no combobox roles | useSearchListNav.ts:56-62; CompanySearchInput.tsx:70-77,204; LocationInput.tsx:55-62,158; ContactPhoneInput.tsx:72-79,191; PlanSearchBox.tsx:60-61; GlobalSearch.tsx:237; Sidebar.tsx:250-263 | Extend the hook (status text, blur close, Escape only when open); give GlobalSearch the roles. | Open
A-42 | Accessibility | P2 | S | Focus and announcement gaps after state changes | Post-submit confirmation replaces the wizard with no focus or announcement (NewConnectionWizard.tsx:80); sidebar toggles unmount the focused button (NavLogoToggle.tsx, PersonaSwitcher.tsx:110-114); mobile drawer has no dialog behaviour (Sidebar.tsx:198-211); route title set once at 150 ms so lazy/data headings keep the generic title (useRouteAnnouncer.ts:26-33); Sales has no h1; async results (FibreReadinessBanner, scans, searching) are visual only; Qnomy Finish/Abandon act immediately | Focus the confirmation h1; focus the counterpart toggle; MutationObserver/usePageTitle; LiveStatus component; confirm Abandon (round-1 A-03/A-11). | Open
A-43 | Accessibility | P2 | S | Field and icon contrast, weak focus cues, hidden file inputs, signature pad, modal naming, lang attribute | --field-border 1.32:1, --field-icon 2.85:1 (round-1 A-05); highlight 1.06:1 (Select.tsx:226, C360Kit.tsx:429, GlobalSearch.tsx:256-290); underline-only focus (C360ProductsServices.tsx:361, PhoneNumberInput.tsx:204); file inputs tabbable and unnamed (CafDocumentUpload.tsx:133, AdditionalDocumentsUpload.tsx:139, PostpaidDiscountsPanel.tsx:140); SignaturePad.tsx:60-69; Modal.tsx:44/Drawer.tsx:66 aria-label not labelledby, no inert/scroll lock; App.tsx:43-45 lang=ar over English; navigation done through role=button rows (OrdersSection.tsx:17, TicketsSection.tsx:53, LeadListView.tsx:64, MySalesOrders.tsx:88, TaskListView.tsx:159) and window.location (HeaderContextChips.tsx:79) | Token fix; shared active-option ring; FileTrigger; label the canvas; dialog naming + inert; keep lang=en; real links for navigation. | Open
B-03 | Behaviour | P2 | M | Detail screens treat 'not loaded yet' as 'not found' | TaskDetailView.tsx:91, LeadDetailsView.tsx:54, TicketDetail.tsx:30, TicketApprovalReview.tsx:101, OrderApprovalDetail.tsx:~511, SimSwapQueueScreen.tsx:88 | useEntityById returning {status}; shared EntityNotFound with a Back link. | Fixed | EntityMissing + useKindPending on lead, task, ticket, approval, order approval and SIM swap detail screens.
B-07 | Behaviour | P2 | S | Enter bubbles from drawers/modals into the wizard step's Continue handler | GuidedActivationWizard.tsx:207,255 (onKeyDown on the step panel); Drawer/Modal are not portaled. Unverified in browser. | Portal overlays, or stop key propagation in the overlay root. | Open
B-08 | Behaviour | P2 | S | Toasts have no timer; outside click or Escape clears all, including errors, and closes the top dialog too | capabilities/Toasts/Toast.tsx:147-160; only 8 of 69 pushToast calls carry a key | Auto-dismiss success/info (6 s), sticky errors, Escape owned by the top overlay, keyed dedupe by default. | Open
B-09 | Behaviour | P2 | M | Overlay conventions differ: forms in Modal vs Drawer, footer in body vs footer prop, Cancel/Back wording, backdrop click closes Modal but not Drawer | ActivationCompleteScreen.tsx:252 (form in Modal); Lead/Order/SIM-swap/Ticket drawers put buttons in the body; TicketDrawers.tsx:72 'Back' as cancel; Modal.tsx:37 vs Drawer.tsx:54 | FormDrawer (sticky footer, Cancel left, primary right) and ConfirmDrawer; one backdrop rule; scroll lock. | Open
B-10 | Behaviour | P2 | M | No dirty-form guard on edit drawers; Escape/X silently discards; TicketCreationModal X keeps the draft but Cancel resets | DemographicEditDrawer, AddressEditDrawer, ContactEditDrawer, BillingAccountPage drawers, TicketCreationModal.tsx:187 vs :287; useState(props) seeds go stale (DemographicEditDrawer.tsx:36-41) | useUnsavedChangesGuard inside FormDrawer. | Open
B-11 | Behaviour | P2 | M | Destructive actions are inconsistent: some confirm, some are one click, reasons and variants differ | No confirm: lead reassign (LeadDetailsView.tsx:211-225), ticket close (TicketActionsCard.tsx:74), task close (TaskDetailView.tsx:109), Qnomy Finish/Abandon (SessionReferenceNumbers.tsx:178,218,386), AutoPay->Invoice. Lead reject is primary with a !text-danger hack (:194); abandon-on-leave uses auto-text (useWizardDraftActions.ts:165) | ConfirmDrawer({severity, requireReason}); verbs Reject / Return for correction / Discard / Cancel. | Open
B-12 | Behaviour | P2 | M | Wizard Continue is disabled with no reason, in every journey | wizardNavigation.ts:20, WizardFooter.tsx:~45; isValid returns boolean | isValid returns {ok, blockers}; footer shows the reason (aria-describedby). | Open
B-13 | Behaviour | P2 | S | Required-field marking uses three conventions; internal rule ids appear in labels | Asterisk (Input/Select); '(required)' x8 (TicketDrawers.tsx:35,46,70,78, WizardDialogs.tsx:53, OrderApprovalDetail.tsx:715); nothing (Textarea has no required prop); labels like 'RES-01/02', 'ESC-05', 'BR-060' in TicketDrawers.tsx:36-87 | Asterisk everywhere; add required to Textarea/Select; remove rule ids from UI text. | Open
B-14 | Behaviour | P2 | M | Form validation is almost entirely 'disable the button'; edit drawers validate nothing; no type=email/tel, inputMode or autoComplete | Only 4 onBlur validators; ContactSection.tsx:~190, BillingAccountPage.tsx:~190, DemographicEditDrawer age fields; Enter-to-submit in 5 places only | FormField + useFormValidation (touched -> validate on blur -> revalidate on change); useEnterToSubmit in FormDrawer. | Open
B-15 | Behaviour | P2 | L | Journeys differ unintentionally: only New Connection and Fixed Activation have Save & Exit, Abandon, customer lock and customer view; seven others have none and complete with a toast + redirect | NewConnectionWizard.tsx:85-99, FixedActivationWizard.tsx:35-44 vs NewPrepaidWizard, InstallationActivationWizard, NewPreToPostWizard, BaseManagementWizard, NewMnpWizard, NewSimSwapWizard, PassportToQidWizard | Make the exit controls, lock and ActivationComplete defaults of GuidedActivationWizard. | Open
B-16 | Behaviour | P2 | M | Navigation: Back is navigate(-1); tabs are not in the URL; detail ids use two schemes; unknown URLs show three different not-found screens | Breadcrumbs.tsx:58; Tabs.tsx:39; ?id= vs /tasks/:taskId; ModuleScreenList.tsx:66 vs ScreenNotYetBuilt.tsx vs NotFound.tsx; no scroll reset on route change (App.tsx) | useTabParam, BackLink with fallback, one EntityNotFound, scroll+focus reset. | Open
B-18 | Behaviour | P2 | S | Enterprise account creation writes a different id field than readers use; 'CR verified' is set by pressing Search | modules/enterprise-iot-b2b/screens/EnterpriseAccountCreation.tsx:32-44 (accountId ACC-... vs enterpriseAccountId ENT-ACC-...) | Write the canonical field; remove the fake verification. | Open
B-19 | Behaviour | P2 | S | Demo data is in-memory but the UI never says so; persisted drafts point at deleted rows after reload; resume silently restarts at step 0 | mockDataEngine.ts:94; workflowStore (session) vs memory orders; useJourneyStartResume.ts | Say so (banner), and drop dangling drafts at boot or tell the user. | Open
B-20 | Behaviour | P2 | S | Production UI ships test controls | TicketActionsCard.tsx:~80-85 'Simulate -> send to approval (test)'; WinCashPaymentStep.tsx:155-167 simulators; demoContentColumn.tsx:13 'Demo Content' column on orders lists | Gate behind demo-only / VITE_SHOW_DEMO. | Open
D-07 | Data/config | P2 | M | Mock data drift: status vocabularies, two order schemas, money-field casing, three actor-id namespaces, dates, dangling references | orders: Complete/Completed/Pending/Open/Draft; tasks 'In Progress' vs 'In-Progress'; lowercase vocabularies in appointments, bills, mnp-*; orders.json two generations (totalQAR not mrc+nrc in 22 records; ORD-92004 addonIds holds PROD-101); mrcQAR/creditLimitQar/amount; USR-1101 vs AGENT-* vs display names; 34 naive/Z dates, 2 DD/MM dob; installed-assets orderNumber ORD-90022/90023 missing; qtickets null customerId | Normalise and add a referential-integrity test. | Open
D-08 | Data/config | P2 | M | Business-rule numbers live only in code (or in three places); config contradicts itself | line caps ruleEngine.ts:38,169 vs BR-288; passport cap BR-108 vs BR-347; credit limit 1000/50 repeated ruleEngine.ts:316-321, EligibilityGateStep.tsx:179, BaseManagementWizard.tsx:124; HRN 100 in 3 places; VAT 0.05 assumed; stale '346 rules' comment (349 exist); BR-02 vs BR-002 ids | public/config/rule-parameters.json read by engines, plus a test tying values to rule text. | Open
D-10 | Data/config | P2 | S | Boot and config failure handling | App.tsx:~43 bare error with no Retry; configEngine.ts:137-152 .catch(() => []) hides approval-matrix and customer360 fields; deploy/nginx.conf try_files returns HTML for missing JSON; ~2.2 MB of config + mock downloaded before the login page | Retry action, warn on optional fallback, 404 for /config and /mock-data, lazy-load per entity. | Open
D-11 | Data/config | P2 | S | Store versioning gaps | themeStore, regionStore, customerVerificationStore, workflowStore, customerContextStore have no version/migrate; customerVerification persists in localStorage across restarts with no expiry | version + migrate; test hydration of old payloads. | Open
D-12 | Data/config | P2 | M | Test coverage and lint depth are thin | No tests for router/registry parity, journey catalogue, 7 journeys, mockDataEngine writes, store hydration, resetSession, serviceCall, capability registry, 11 of 32 primitives; weak tests (nav route check only tests a string prefix, rules 'do not throw'); lint 91 warnings pass CI; no strict/noUncheckedIndexedAccess flags written; no typecheck/lint:ci scripts, no engines | Guards G1-G12 in report section 12; oxlint --deny-warnings; enable eqeqeq, no-console, jsx-a11y rules. | Open
D-13 | Data/config | P2 | S | Generated artefacts and docs drift | Test_Data_Reference.xlsx no longer exists (live file '01 Test_Data.xlsx'; generator writes the old name, drops 3 hand-built sheets); '02 Customer-Inventory.xlsx' differs from Customer-Inventory.xlsx; UI_Component_Route_Inventory and Reusable_Capabilities_Inventory older than 196-213 source files; design-tokens.json still cited (update-capability SKILL.md:47, audit.py, Design Principles reference); README.md is stock Vite; reference/README.md lists missing folders; registry.json 22 vs 30 capability entries; 114 MB xlsx not ignored | Regenerate, choose one naming convention, fix references, gitignore the large workbook. | Open
D-14 | Data/config | P2 | S | Routes: 20 catalogue screens unregistered, 124 of 213 in no feature, duplicate journey targets overstate 'available', slug/module mismatches, slugs up to 60 characters | 13 features show Planned only; mob-portin-new/mob-fnp-change, fib-create-ticket/connectivity-issue/complaint share screens; SCR-016/037/042/113/164 sit under another module's slug; SCR-061 slug ends '-activities-a'; build size: 3 chunks >300 kB; .env* not ignored, CI builds with demo content | Report as counts; slug/shape test; split capabilities and Customer 360 chunks; VITE_SHOW_DEMO=false CI build. | Open
S-05 | Structure | P2 | M | Handler contracts differ: onChange(value) vs event vs multi-arg; six onSelect shapes; onRowClick vs onSelect vs onPick | Select.tsx:17 and PhoneNumberInput.tsx:32 are event-based (77 call sites do e.target.value) while FilterSelect and all steps are value-based; NumberSelection.tsx:20, SimSerialScanner.tsx:26, CpeSerialScanner.tsx:15, BillLimitEditor.tsx:15 multi-arg; GridTable onSelect, CustomerActionsMenu onPick | onChange(value) for non-native components; onSelect(item); onRowClick for rows. | Open
S-06 | Structure | P2 | S | Button API carries 6 dead legacy variants and a compact alias; wrappers add only a boolean | Button.tsx:14-17,144-159 (primary-rect, primary-pill, ghost-rect, glass-pill, content-ghost-pill, secondary-rect: 0 call sites); compact 79 uses vs size 0; ActionButton/HeaderButton primary prop (C360Kit.tsx:141, TelesalesKit.tsx:61); KebabButton vs IconButton bordered | Delete legacy variants; compact -> size=sm; drop the boolean wrappers. | Open
S-07 | Structure | P2 | M | Prop vocabulary: helperText/hint/description/sub/subtitle/subtext/caption; tabs use active/activeKey/activeTab; className not accepted by most primitives | Input.tsx:7 helperText vs QidInput.tsx:59 hint vs GlobalSearch.tsx:15 sub vs MetricCard.tsx:4 subtext; Tabs.tsx:38 activeKey, SegmentedTabs.tsx:23 active, PlanTabStrip.tsx:6 activeTab; Badge/Modal/Tabs/Tooltip/DataTable have no root className | helperText for fields, description for cards/rows, value/onChange for tabs, className on every primitive root. | Open
S-08 | Structure | P2 | L | Missing shared primitives for patterns re-implemented 5-14 times | Combobox/Listbox + useOutsideClick (11 click-outside listeners; Select, FilterSelect, PhoneNumberInput, CompanySearchInput, LocationInput, ContactPhoneInput, GlobalSearch, PlanSearchBox); Avatar x5; key-value rows ~14 copies (Field x6, Row x3, KV, DetailRows, DetailRow, FieldRow...); stat tiles x7; Pill x2 + Badge; icon paths 314 literals / 200 distinct / 12 icon maps | Combobox, useOutsideClick, Avatar, DescriptionList/FieldRow, KpiTile, icons.ts registry. | Open
S-09 | Structure | P2 | M | Order submission logic is copy-pasted across 3 builders and 6 inline wizard submits | submitNewConnectionOrder.ts:28, submitPrepaidOrder.ts:38, submitFixedActivationOrder.ts:25, NewMnpWizard.tsx:73-93, NewPreToPostWizard.tsx:41, BaseManagementWizard.tsx:115,129, NewSimSwapWizard.tsx:120, PassportToQidWizard.tsx:105, NewFwaWizard.tsx:30; B2B2C predicate at submitNewConnectionOrder.ts:84,154 and submitFixedActivationOrder.ts:43,56; ConfirmedOrder defined twice | submitJourneyOrder / buildOrderRecord in engines/; isB2b2cOrder(). | Open
S-10 | Structure | P2 | S | 37 hand-built id snippets Date.now().toString().slice(-6); suffix repeats every ~16 minutes | 27 files, e.g. submitNewConnectionOrder.ts:134, useWizardDraftActions.ts:119,133, slaEscalationSweep.ts:51,60; other variants use Math.random (activityEngine.ts:42) | lib/ids.ts newId(prefix). | Open
S-11 | Structure | P2 | L | Domain types are redeclared per file and data access is untyped | Order x5, Ticket x6, CustomerRecord x5, Product x4, Activity x4, AddressRecord x3...; mockDataEngine.list<{inline}> x34; as unknown as x49; values.X as T x164; Record<string, unknown> x200; duplicate unions (FibreServiceability = FixedRfsStatus, AccessMode = FieldVisibility, Tone/PillTone) | types/entities.ts keyed by EntityKind; typed list/get/records; typed wizard values. | Open
S-12 | Structure | P2 | M | Effects: 21 set-state-in-effect, 7 exhaustive-deps (+43 suppressions), ~15 uncancelled .then(setX), component created in render | oxlint output; CompanySearchInput.tsx:67, AppointmentBookingStep.tsx:43, PrepaidCheckoutStep.tsx:69-71; ScreenRouteResolver.tsx:14 (getScreenComponent in render) | useEntityList/useAsync with cancel; derive state during render or use key; fix the resolver. | Open
V-05 | Visual | P2 | S | Page and header insets differ: 16 / 20 / 24 / 32px; page container deviations | PersonaSwitcher.tsx:101 px-4, Breadcrumbs.tsx:43 px-6, PageHeader.tsx:26 px-5, content p-8; SalesWorkspace.tsx:52 + LeadListView.tsx:47 (double padding); ConnectionDetailsPopup.tsx:26 cuts the header band; border greys #e0e0e0 vs #c9ced4 on adjacent bands | One inset (px-8) and one band border colour. | Open
V-08 | Visual | P2 | S | Border, radius and elevation roles are unclear; modal has no border, tooltip carries the modal shadow, two scrims | DataTable.tsx:131 #e0e0e0 next to cards #c9ced4; Modal.tsx:40 raised with no border; tooltip uses --elev-raised (60px blur); --black-80 scrim (Modal.tsx:37, Drawer.tsx:58) vs --scrim 40% (Sidebar.tsx:202); Sidebar.tsx:224 shadow-xl; Toast.tsx top-[calc(4rem+0.75rem)] hard-codes the header height | Cards/bands field-card-border, tables/nav --border; two elevation levels; one scrim; --header-h token. | Open
V-12 | Visual | P2 | S | Print and the customer-view mirror | index.css:204-218 prints dark tokens in dark mode (white-on-white); no @page, print-color-adjust, header repeat or break-inside; mirror stays in the stored theme, has no max-width and mounts the hidden shell | Re-declare light tokens in @media print; force light in the mirror. | Open
V-14 | Visual | P2 | S | Heading structure and page-header patterns | SalesWorkspace.tsx:53 h2 before the nested LeadListView h1; CustomerMirrorPanel.tsx:25 h2 only; two header patterns (PageHeader band vs card with 32px h1: LeadDetailsView.tsx:90-93, TicketHeaderCard.tsx:18-19); ~35 files skip heading levels; emoji glyphs for UI (TicketHeaderCard.tsx:21, ContactPhoneInput.tsx:130) | PageHeader everywhere; heading components that encode the role table. | Open
X-01 | Content | P2 | M | Case convention: ~56% Title Case vs ~40% sentence case; 81 labels differ only by case | Title clusters: telesales/*, C360*, lead-management, ticket drawers; sentence clusters: administration (27 vs 1), profile, auth, CrossSellOffers, zoneSpecs.ts:40-54, OrderApprovalDetail sections. e.g. 'View All' x32 / 'View all' x4; 'Credit Limit' x12 / 'Credit limit' x4; 'Alert & Risks' (Customer360Layout.tsx:348) vs 'Alerts & Risks' (:470) | Sentence case everywhere (decision needed - round-1 L-06); fix the 81 duplicates first. | Open
X-03 | Content | P2 | S | Save / draft / submit labels overlap: 'Save & Finish' submits the order, 'Save & Exit' saves a draft | WizardFooter.tsx:51; WizardTitleBand.tsx:40; WizardDialogs.tsx:84-139; plus Save Changes x7, Save x4, Submit approval, Confirm rejection, Apply, Update | Save changes / Save draft / Submit order. | Open
X-04 | Content | P2 | S | Reject / Return / Drop / Abandon / Remove / Clear are used for overlapping meanings | OrderApprovalDetail.tsx:674-729 (drawer 'Reject Order' for both correction and drop); SimSwapQueueScreen.tsx:156,169 'Drop Order' under 'Reject Task'; 'Abandon Order' vs 'Abandon Journey' (WizardDialogs.tsx:42,136); 'Abandoned' as a button label (SessionReferenceNumbers.tsx) | Reject, Return for correction, Discard. | Open
X-05 | Content | P2 | M | Terminology drift: customer/contact/subscriber/applicant/user; MSISDN vs mobile number vs phone; ticket vs Trouble Ticket vs issue; Add-on/Add-On/Add On | OrderApprovalDetail.tsx:~644 'Contact:' vs 'Customer'; Business360Page.tsx:93 'Subscriber / account ID'; CustomerSearchPage.tsx:42 vs :66 vs CustomerSearchResults.tsx:13-19; QnomyTicketHistory.tsx:146 'Ticket Number' is a queue ticket; MobileSection.tsx:21-22; 'persona' leaks into UI (BellNotificationsSection.tsx:157) | One term per concept (style guide in report). | Open
X-10 | Content | P2 | S | Message wording is inconsistent: 'Please …' vs imperative, try again vs Retry, missing end punctuation, duplicate texts that differ | ProductPlanStep.tsx:73 and FixedStepViews.tsx:182 'Please Select a Plan.'; WinCashPaymentStep.tsx:139; 'Not authorised …' without period (Customer360Layout.tsx:573, BillingAccountPage.tsx:46, InvoiceActions.tsx:31); 'Invalid or expired code.' vs '… verification code.'; 16 of 60 toasts lack a period; 'Lead x has been created' vs 'Lead x created' | Style-guide rules (report section 11). | Open
X-12 | Content | P2 | M | Currency, date, phone and masking formats still bypass the shared formatters | ~31 suffix 'N QAR' (billingResolvers.tsx:21-37, Customer360Layout.tsx:593,598, BillingAccountPage.tsx:170, penaltyViewResolvers.tsx:95), ~40 hand-built 'QAR ${…}'; BaseManagementWizard.tsx:93 'QAR 1000'; MsisdnPicker.tsx:356 en-US + nbsp; formatDate pads the day (format.ts:30 docstring says '12 Mar') while TaskListView.tsx:39, CustomerProfileHeader.tsx:69 do not; customer360Engine.ts:336 en-US; phones printed raw (+97455512001) except ContactPhoneInput; maskEmail (***@****) vs maskAllButLast4 (••••1234) | Route everything through lib/format.ts; fix the docstring; one phone and mask format. | Open
X-15 | Content | P2 | L | Mirroring for Arabic is cosmetic: 302 physical-direction utilities, 0 logical, directional glyphs fixed, UI text is English | ml- 26, mr- 8, pl- 33, pr- 27, left- 30, right- 48, text-left 57, text-right 37, border-l 20; no rtl: variants; hard-coded arrows/chevrons (Breadcrumbs.tsx:6-7); App.tsx:37-45 sets dir and lang=ar over English text | Logical utilities (ms-/me-/ps-/pe-/start/end/text-start/text-end); flip icons; keep lang=en until translated. | Open
B-17 | Behaviour | P3 | M | Tables: sort/page state is local and lost; no search debounce; pager renders every page number; generic empty copy | DataTable.tsx, Pager.tsx, GlobalSearch.tsx (no debounce, fires from 1 char), LeadListView.tsx:33-40 ('my' scope is a no-op) | useTableState (URL params), bounded pager, filtered-empty message. | Open
S-13 | Structure | P3 | M | Mixed data access and persistence conventions | 69 files use mockDataEngine directly, 51 useEntityStore, 15 both; raw fetch in customerTypeModel.ts:54; Tabs.tsx:84 writes localStorage directly; customerContextStore mixes persist with hand-written storage; whole-store subscriptions (Toast.tsx:125, HeaderContextChips.tsx:29, Sidebar.tsx:69) | useEntityStore for reads, engines for writes; zustand persist only (vfq-<name>-store); selectors. | Open
S-14 | Structure | P3 | M | Files: 41 only-export-components warnings; multi-component kit files; no path alias (513 imports go three levels up); dated-history comments (353) | C360Kit.tsx (20 exports, 7 warnings), TelesalesKit.tsx (15), offerCardParts.tsx (12), previews.tsx (10), TelesalesOverview.tsx; tsconfig/vite have no paths; Button.tsx is 130 comment lines of 187 | Move constants to *Model.ts; @/ alias; strip dated history; keep the current rule only. | Open
S-15 | Structure | P3 | S | Stale comments and READMEs contradict the code | Button.tsx:7-15,46-49,125,141-153 (ghost-rect, #FF4D4D, 8px); SessionReferenceNumbers.tsx:389; OrderConfirmationScreen.tsx:130-135; tokens.css:323; src/README.md:15 (empty steps/ dir), :17 (lib/), :63 (GridTable); capabilities/README.md:46-47 (cycle-free claim); data/README.md:8 (loginMetrics.ts) | Update; delete empty modules/new-connection/steps/. | Open
V-06 | Visual | P3 | S | Card padding and gaps vary by area; same-role sections use mb-4/mb-6; heading margins mb-1/2/3 | p-4 (45) / p-5 (36) / p-3 (9) / p-6 (7); administration/profile/tasks p-5, customer360 p-4 | p-5 page cards, p-4 dense tiles, p-6 wizard/modal; gap-6 between cards. | Open
V-07 | Visual | P3 | S | Icons: sizes w-3.5/4/4.5/5/6, strokes 1.5-3, selected-card check badge in 5 geometries, close glyph 20px vs icon button 16px | IdentityDetailsCard.tsx:26 w-[18px]; CloseButton.tsx:18 vs IconButton.tsx:32; Checkbox.tsx:56, PanelIcon.tsx:9, StepSummarySection.tsx:37; check badges at QidInput.tsx:173, MsisdnPicker.tsx:607,568, AddonsPicker.tsx:190, DiscountCard.tsx:24, CafSignatureCapture.tsx:363; inline svg in 5 places that should use Icon | 16/18/20 sizes by context, stroke 2 (3 for checks), one SelectedTick. | Open
V-10 | Visual | P3 | S | Light-mode contrast near-misses | --customer-view-fg 3.33:1 (WizardStepHeader.tsx:56, POSTPAID_PILL), --link on page-bg 4.43:1, --tag-blue-fg 4.28:1, tag-green 4.36:1, error text #e60000 on page-bg 4.37:1, text-link on charcoal 3.21:1 (LoginPage.tsx:233), disabled/field icon #999 2.85:1 | Token tweaks (accent-text for error text, lighter on-dark link). | Open
V-11 | Visual | P3 | S | 78% of hover states have no transition; Tailwind default transition is not bound to the motion tokens; entrances are missing | ~90 of ~116 hover: class strings lack transition (PersonaSwitcher.tsx, Toast.tsx, C360Overview.tsx, LoginPage.tsx); Drawer backdrop does not fade; Modal/Select/popover/toast have no enter transition | Map --default-transition-* to --motion-fast/--ease-standard; add transition-colors to interactive hovers; one entrance. | Open
V-13 | Visual | P3 | S | Brand: login renders 'Vodafone' text twice instead of the wordmark; Google Fonts loads all weights + italics; assets duplicated/unoptimised | LoginPage.tsx:25-29,152,259; index.html:5-8; public/Vodafone_Logo.svg unreferenced, brand/vodafone-logo-big¦small.svg duplicates; login-bg.jpg 505KB; favicon SVG only | Shared Logo component; self-host 6 weights; prune assets (round-1 L-12). | Open
X-11 | Content | P3 | S | Empty, loading and placeholder text are not uniform | 'No X on file.' (~46) vs 'Nothing on file.' vs 'No X for this customer.' vs 'No X match…' (6 phrasings); empty values '-' (~310) vs None vs Not on file vs Not recorded; 'Checking...' (ActivationCompleteScreen.tsx:236), 'Searching', 'Loading' vs 'Loading…'; 6 placeholders end '...' | 'No x yet.' / 'No x match your filters.'; the ellipsis character. | Open
X-13 | Content | P3 | S | Spelling mixes British and American | authorised x27 vs authorized x17 (contactInformationResolvers.tsx:20-62, C360ContactIdentity.tsx:91 vs :160), 'Call Center' (previews.tsx:53, customer360-fields.json), 'Trade License' (EnterpriseAccountCreation.tsx:71), 'Catalog Sync' (HeaderContextChips.tsx:66), 'CCT-Rude Behavior', ROLE-09 'Authorized Officer' | British throughout. | Open
X-14 | Content | P3 | S | Abbreviations and vendor names are never expanded in the UI | MOI (15), KYC, SLA (17), CPE, B2B2C (26), MADA (18), EBU (13), BRM, FNP, ICCID; HRN/CAF/TON/WFM/RFS partly; 'Qnomy', 'Surepay', 'WinCash', 'Siebel' leak | Expand on first use or via tooltip; link the glossary. | Open