## Priority Queue
Priority Rank | Catalogue # | Journey Name | Journey Category | Catalogue Type | Confidence % | Criticality | Complexity | Est. Hours | Target Week | Notes
1 | 71 | MOI Validation | Support | Workflow/Task | 95 | High | Medium | 2 | Week 1
2 | 8 | Prepaid to Postpaid | Sales | Workflow/Task | 94 | High | Medium | 2 | Week 1
3 | 41 | Create Ticket | Support | Workflow/Task | 88 | High | Medium | 2 | Week 1
4 | 110 | Manage Bill Limit | Manage | Workflow/Task | 88 | High | Medium | 2 | Week 1
5 | 154 | Changing Bill Cycles | Manage | Workflow/Task | 88 | High | Medium | 2 | Week 1
6 | 23 | Plan Change (Upgrade/Downgrade) | Support | Workflow/Task | 85 | High | Medium | 2 | Week 1
7 | 117 | PMN Suspension | Manage | Workflow/Task | 85 | High | Medium | 2 | Week 1
8 | 89 | TON Trouble Ticket Approval | Support | Workflow/Task | 80 | High | Medium | 2 | Week 2
9 | 136 | Update Credit Limit | Manage | Workflow/Task | 80 | High | Medium | 2 | Week 2 | Represents 3 near-duplicate catalogue rows (#136/#146/#147, all "Credit Limit"); one diagram covers all three.
10 | 30 | Adjustment Approval | Support | Workflow/Task | 75 | High | Medium | 2 | Week 2
11 | 124 | Resume Suspension | Manage | Workflow/Task | 75 | High | Medium | 2 | Week 2
12 | 99 | Handle Port Out Tickets | Support | Workflow/Task | 70 | High | Medium | 2 | Week 2
13 | 25 | TON | Support | Workflow/Task | 95 | High | Complex | 3 | Week 2
14 | 116 | FDO Order | Manage | Workflow/Task | 95 | High | Complex | 3 | Week 2
15 | 13 | RFS/Fiber Home Move | Sales | Workflow/Task | 88 | High | Complex | 3 | Week 2
16 | 22 | Postpaid to Prepaid | Support | Workflow/Task | 85 | High | Complex | 3 | Week 2
17 | 159 | Disconnect MSISDN (Prepaid, Postpaid, Fiber, FWA) (Normal & Star Number Disconnection) (normal & with suspension status) | Disconnect | Workflow/Task | 82 | High | Complex | 3 | Week 2
|  | TOTAL | [5 empty] | 39

## Recommendation
Recommendation: trim to a 12-diagram Tier 1 batch for the 2-week window
After deduplication, 17 distinct candidates remain, totaling 39.0 estimated hours — achievable in
2 weeks but leaves little slack alongside Actions 1.5.4-1.5.7. Suggested approach: run all 8 'Medium'
complexity candidates first (16 hours, all fit Week 1) since they are faster and still High-confidence/
High-criticality, then take the top 4 'Complex' candidates by confidence (TON, FDO Order, RFS/Fiber Home
Move, Postpaid<->Prepaid) into Week 2, deferring the remaining Complex items (Disconnect MSISDN) to a
later batch given its scope overlaps significantly with the existing UJ diagrams' disconnection sub-flows.
None of this is final — the ranked list on the 'Priority Queue' tab is the full candidate set. Please confirm:
1. Accept all 17 candidates, or trim to a subset (and which ones)?
2. OK to treat #136/#146/#147 as one diagram (Credit Limit), or generate separately?
3. Any specific journeys you want prioritized regardless of this ranking?